# ASC Accreditation Roadmap

## 12-Month Compliance Calendar & Deliverable Tracker

Product: Ambulatory Surgery Center Compliance Manual — Tier 1
Version: 1.0
Applicable Standards: CMS Conditions for Coverage (42 CFR Part 416), AAAHC Standards, State Licensure Requirements

## How to Use This Roadmap

This document provides a month-by-month action plan for achieving and maintaining ASC accreditation. Each month contains:

- Compliance milestones tied to CMS and AAAHC requirements

- Required documentation you must prepare or update

- Submission deadlines and internal due dates

- Responsible party assignments for small teams (1–2 compliance staff)

Tip for Small Teams: Block 4–6 hours per week exclusively for compliance work. Treat it like a clinical shift — non-negotiable.

## Annual Compliance Overview

| Quarter | Focus Area | CMS Reference | AAAHC Chapter |
| --- | --- | --- | --- |
| Q1 (Months 1–3) | Foundation & Gap Analysis | 42 CFR §416.41–416.52 | Chapters 1–5 |
| Q2 (Months 4–6) | Policy Development & Staff Training | 42 CFR §416.50–416.54 | Chapters 6–10 |
| Q3 (Months 7–9) | Implementation & Mock Surveys | 42 CFR §416.44–416.48 | Chapters 11–15 |
| Q4 (Months 10–12) | Final Prep, Submission & Continuous QI | 42 CFR §416.43 | All Chapters |

## Month 1: Baseline Assessment & Gap Analysis

### Compliance Milestones

- ☐ Complete facility-wide gap analysis against current CMS Conditions for Coverage

- ☐ Identify all areas of non-compliance or partial compliance

- ☐ Establish compliance committee (even if 2 people — formalize it with meeting minutes)

- ☐ Verify current state licensure status and renewal dates

### Required Documentation

| Document | CMS Reference | Status | Due Date | Owner |
| --- | --- | --- | --- | --- |
| Gap Analysis Report | §416.41 (Governing Body) | ☐ Not Started | Month 1, Week 2 | Compliance Lead |
| Compliance Committee Charter | §416.41 | ☐ Not Started | Month 1, Week 3 | Administrator |
| Current License Inventory | State Requirements | ☐ Not Started | Month 1, Week 1 | Compliance Lead |
| Organizational Chart | §416.41 | ☐ Not Started | Month 1, Week 2 | Administrator |
| Governing Body Bylaws Review | §416.41 | ☐ Not Started | Month 1, Week 4 | Administrator |

### Submission Deadlines

- Internal: Gap analysis complete by end of Week 2

- External: None this month (planning phase)

- State: Verify licensure renewal date; if within 6 months, begin renewal paperwork immediately

### Action Items for Small Teams

- Download the latest CMS State Operations Manual, Appendix L (ASC interpretive guidelines)

- Print AAAHC standards handbook — tab each chapter for quick reference

- Create a shared digital folder structure mirroring accreditation chapters

- Schedule recurring weekly 1-hour compliance huddle

## Month 2: Governing Body & Administrative Framework

### Compliance Milestones

- ☐ Establish or update Governing Body structure and meeting schedule

- ☐ Document transfer agreement(s) with local hospital(s) — or physician admission privileges

- ☐ Review and update facility bylaws

- ☐ Verify medical director qualifications and appointment documentation

### Required Documentation

| Document | CMS Reference | Status | Due Date | Owner |
| --- | --- | --- | --- | --- |
| Governing Body Meeting Minutes (template) | §416.41 | ☐ Not Started | Month 2, Week 1 | Administrator |
| Transfer Agreement (current, signed) | §416.41(b) | ☐ Not Started | Month 2, Week 3 | Administrator |
| Medical Director Credentials File | §416.45 | ☐ Not Started | Month 2, Week 2 | Compliance Lead |
| Bylaws (updated, board-approved) | §416.41 | ☐ Not Started | Month 2, Week 4 | Administrator |
| Disclosure of Ownership (CMS-855B) | §416.41 | ☐ Not Started | Month 2, Week 2 | Administrator |

### Submission Deadlines

- Internal: All governing body documents finalized by Week 4

- External: Transfer agreement must be executed (signed by both parties) — no CMS deadline but required at survey

- State: Check if state requires separate transfer agreement filing

### Critical Notes

CMS Hot Button: Transfer agreements are one of the top 5 deficiency areas. Ensure the agreement is current (not expired), signed by authorized representatives at both the ASC and hospital, and specifies the hospital will accept transfers. If using physician admission privileges instead, maintain current privilege verification letters for every physician on your roster.

## Month 3: Patient Rights & Quality Assessment

### Compliance Milestones

- ☐ Develop or update Patient Rights policy and notice

- ☐ Establish Quality Assessment and Performance Improvement (QAPI) program

- ☐ Create grievance/complaint resolution procedure

- ☐ Develop informed consent process and templates

- ☐ Establish advance directive policy

### Required Documentation

| Document | CMS Reference | Status | Due Date | Owner |
| --- | --- | --- | --- | --- |
| Patient Rights Policy & Notice | §416.50 | ☐ Not Started | Month 3, Week 2 | Compliance Lead |
| QAPI Program Description | §416.43 | ☐ Not Started | Month 3, Week 3 | Quality Lead |
| Grievance Policy & Log Template | §416.50(a) | ☐ Not Started | Month 3, Week 2 | Compliance Lead |
| Informed Consent Templates (by procedure) | §416.50(a) | ☐ Not Started | Month 3, Week 4 | Clinical Lead |
| Advance Directive Policy | §416.50(a)(2) | ☐ Not Started | Month 3, Week 3 | Compliance Lead |
| QAPI Meeting Minutes Template | §416.43 | ☐ Not Started | Month 3, Week 3 | Quality Lead |

### Submission Deadlines

- Internal: QAPI program description approved by Governing Body by Week 4

- External: None — but QAPI must be active and demonstrable at survey

- State: Some states require patient rights posted in specific languages — verify local requirements

## Month 4: Infection Control Program

### Compliance Milestones

- ☐ Appoint Infection Control Officer (can be dual-role for small ASCs)

- ☐ Develop comprehensive Infection Control Program

- ☐ Establish surveillance, tracking, and reporting protocols

- ☐ Verify sterile processing procedures and documentation

- ☐ Conduct baseline infection control risk assessment

### Required Documentation

| Document | CMS Reference | Status | Due Date | Owner |
| --- | --- | --- | --- | --- |
| Infection Control Program Manual | §416.51 | ☐ Not Started | Month 4, Week 3 | IC Officer |
| IC Officer Appointment Letter & Qualifications | §416.51(a) | ☐ Not Started | Month 4, Week 1 | Administrator |
| Infection Surveillance Log Template | §416.51(a) | ☐ Not Started | Month 4, Week 2 | IC Officer |
| Sterilization Logs & Biological Indicator Records | §416.51(b) | ☐ Not Started | Month 4, Week 2 | IC Officer |
| IC Risk Assessment (annual) | §416.51 / AAAHC Ch. 9 | ☐ Not Started | Month 4, Week 4 | IC Officer |
| Hand Hygiene Policy | §416.51 | ☐ Not Started | Month 4, Week 1 | IC Officer |
| Antibiotic Stewardship Policy | §416.51 | ☐ Not Started | Month 4, Week 3 | IC Officer |

### Submission Deadlines

- Internal: IC program manual approved by Governing Body by end of Month 4

- External: Report any reportable infections to state health department per state timelines

- CMS: Infection control is surveyed under §416.51 — one of the highest-cited deficiency areas

### Critical Notes

Surveyor Focus Area: Surveyors WILL observe hand hygiene, PPE use, instrument processing, and environmental cleaning during the on-site visit. They will also request 12 months of surveillance data. Start tracking NOW — even if you have zero infections, document that you have zero infections each month.

## Month 5: Pharmaceutical & Medication Management

### Compliance Milestones

- ☐ Develop medication management policies (ordering, storage, dispensing, administration)

- ☐ Verify controlled substance protocols and DEA compliance

- ☐ Establish adverse drug event reporting process

- ☐ Audit medication storage areas (temperature logs, expiration checks, security)

- ☐ Develop medication reconciliation process

### Required Documentation

| Document | CMS Reference | Status | Due Date | Owner |
| --- | --- | --- | --- | --- |
| Medication Management Policy | §416.48 | ☐ Not Started | Month 5, Week 2 | Clinical Lead |
| Controlled Substance Log Template | §416.48 / DEA | ☐ Not Started | Month 5, Week 1 | Clinical Lead |
| Medication Storage Temperature Log | §416.48 | ☐ Not Started | Month 5, Week 1 | Clinical Lead |
| Adverse Drug Event Reporting Policy | §416.48 | ☐ Not Started | Month 5, Week 3 | Clinical Lead |
| Medication Reconciliation Form | §416.48 | ☐ Not Started | Month 5, Week 3 | Clinical Lead |
| Pharmacy Consultant Agreement (if applicable) | §416.48 | ☐ Not Started | Month 5, Week 4 | Administrator |

### Submission Deadlines

- Internal: All medication policies approved by Month 5, Week 4

- External: DEA registration must be current and posted

- State: Verify state pharmacy board requirements for ASC medication management

## Month 6: Environment of Care & Safety

### Compliance Milestones

- ☐ Complete Life Safety Code assessment (NFPA 101)

- ☐ Verify fire alarm and suppression system compliance

- ☐ Conduct fire drill (document it — this is required quarterly)

- ☐ Review and update Emergency Preparedness Plan

- ☐ Verify medical gas system compliance and documentation

- ☐ Complete equipment maintenance inventory

### Required Documentation

| Document | CMS Reference | Status | Due Date | Owner |
| --- | --- | --- | --- | --- |
| Life Safety Code Compliance Report | §416.44 / NFPA 101 | ☐ Not Started | Month 6, Week 3 | Facilities |
| Fire Drill Documentation (quarterly) | §416.44 | ☐ Not Started | Month 6, Week 2 | Safety Officer |
| Emergency Preparedness Plan | §416.54 | ☐ Not Started | Month 6, Week 4 | Administrator |
| Equipment Maintenance Log (all devices) | §416.44 | ☐ Not Started | Month 6, Week 2 | Facilities |
| Medical Gas Inspection Records | §416.44 | ☐ Not Started | Month 6, Week 1 | Facilities |
| HVAC Maintenance & Air Exchange Records | §416.44 | ☐ Not Started | Month 6, Week 2 | Facilities |
| Hazardous Materials Inventory | §416.44 | ☐ Not Started | Month 6, Week 3 | Safety Officer |

### Submission Deadlines

- Internal: Emergency preparedness plan approved by Governing Body by Week 4

- External: Fire marshal inspection must be current (annually in most states)

- State: Verify state-specific life safety requirements — some exceed federal standards

### Critical Notes

Survey Day Reality: Surveyors will physically walk the facility. They check exit signage, fire extinguisher inspection tags, electrical panel clearance (36 inches), crash cart seal integrity, and medication refrigerator temperatures. A single expired fire extinguisher tag can trigger a deficiency. Walk your facility monthly with fresh eyes.

## Month 7: Surgical & Anesthesia Services

### Compliance Milestones

- ☐ Review and update surgical services policies

- ☐ Verify anesthesia services compliance (CRNAs, anesthesiologists, supervision requirements)

- ☐ Audit operative and anesthesia records for completeness

- ☐ Verify post-anesthesia care protocols

- ☐ Confirm discharge criteria documentation

### Required Documentation

| Document | CMS Reference | Status | Due Date | Owner |
| --- | --- | --- | --- | --- |
| Surgical Services Policy Manual | §416.42 | ☐ Not Started | Month 7, Week 3 | Clinical Director |
| Anesthesia Services Policy | §416.42(b) | ☐ Not Started | Month 7, Week 2 | Anesthesia Lead |
| Operative Record Template Audit | §416.47 | ☐ Not Started | Month 7, Week 2 | Clinical Lead |
| Post-Anesthesia Discharge Criteria | §416.42(b)(3) | ☐ Not Started | Month 7, Week 3 | Anesthesia Lead |
| Pre-Operative Assessment Template | §416.42 | ☐ Not Started | Month 7, Week 1 | Clinical Lead |
| Anesthesia Equipment Check Log | §416.42(b) | ☐ Not Started | Month 7, Week 1 | Anesthesia Lead |

### Submission Deadlines

- Internal: All surgical and anesthesia policies approved by Month 7, Week 4

- External: Anesthesia provider credentialing must be current

- State: Verify state scope-of-practice requirements for CRNAs

## Month 8: Medical Records & Health Information

### Compliance Milestones

- ☐ Audit medical record completeness (minimum 10 charts)

- ☐ Verify HIPAA compliance documentation

- ☐ Establish record retention policy

- ☐ Verify authentication requirements for all entries

- ☐ Confirm medical records are available and organized

### Required Documentation

| Document | CMS Reference | Status | Due Date | Owner |
| --- | --- | --- | --- | --- |
| Medical Record Audit Results (10+ charts) | §416.47 | ☐ Not Started | Month 8, Week 3 | Compliance Lead |
| Medical Record Policy | §416.47 | ☐ Not Started | Month 8, Week 2 | Compliance Lead |
| HIPAA Privacy & Security Policies | §416.47 / HIPAA | ☐ Not Started | Month 8, Week 3 | Privacy Officer |
| Record Retention Schedule | §416.47 | ☐ Not Started | Month 8, Week 2 | Compliance Lead |
| Chart Completion Checklist | §416.47 | ☐ Not Started | Month 8, Week 1 | Clinical Lead |
| Business Associate Agreements (current) | HIPAA | ☐ Not Started | Month 8, Week 4 | Administrator |

### Submission Deadlines

- Internal: Chart audit complete by Week 3 with corrective actions identified

- External: HIPAA breach reporting (if applicable) per HHS timelines

- State: Verify state medical record retention requirements (may exceed federal)

## Month 9: Credentialing & Privileging

### Compliance Milestones

- ☐ Audit all physician and provider credential files

- ☐ Verify current privileging for all providers performing procedures

- ☐ Confirm NPDB query completion (within 2 years)

- ☐ Verify licensure, DEA, malpractice insurance for all providers

- ☐ Update credentialing policies and peer review process

### Required Documentation

| Document | CMS Reference | Status | Due Date | Owner |
| --- | --- | --- | --- | --- |
| Credentialing Policy | §416.45 | ☐ Not Started | Month 9, Week 2 | Administrator |
| Provider Credential Files (each provider) | §416.45 | ☐ Not Started | Month 9, Week 3 | Compliance Lead |
| Privilege Delineation Forms (by specialty) | §416.45 | ☐ Not Started | Month 9, Week 2 | Medical Director |
| NPDB Query Verification | §416.45 | ☐ Not Started | Month 9, Week 1 | Compliance Lead |
| Peer Review Policy & Minutes | §416.45 | ☐ Not Started | Month 9, Week 3 | Medical Director |
| Malpractice Insurance Verification | §416.45 | ☐ Not Started | Month 9, Week 1 | Compliance Lead |

### Submission Deadlines

- Internal: All credential files 100% complete by Month 9, Week 4

- External: NPDB queries must be current (within 2 years per AAAHC; CMS expects at initial privileging and reappointment)

- State: Verify state credentialing timeline requirements

### Critical Notes

#1 Deficiency Nationally: Credentialing and privileging deficiencies are the most frequently cited issue in ASC surveys. Every single provider file MUST contain: current license, DEA (if applicable), board certification verification, malpractice insurance, NPDB query, privilege delineation, and peer references. Missing ONE document in ONE file = deficiency.

## Month 10: Mock Survey & Remediation

### Compliance Milestones

- ☐ Conduct comprehensive mock survey (use Survey Readiness Checklist)

- ☐ Document all findings with severity rating

- ☐ Develop Plans of Correction for each finding

- ☐ Begin remediation of all identified deficiencies

- ☐ Conduct staff interviews using surveyor-style questions

### Required Documentation

| Document | CMS Reference | Status | Due Date | Owner |
| --- | --- | --- | --- | --- |
| Mock Survey Report | All sections | ☐ Not Started | Month 10, Week 2 | Compliance Lead |
| Plan of Correction (for each finding) | All sections | ☐ Not Started | Month 10, Week 3 | All Owners |
| Staff Interview Q&A Results | All sections | ☐ Not Started | Month 10, Week 2 | Compliance Lead |
| Remediation Tracking Log | All sections | ☐ Not Started | Month 10, Week 4 | Compliance Lead |
| Updated Policies (corrected items) | Varies | ☐ Not Started | Month 10, Week 4 | All Owners |

### Submission Deadlines

- Internal: Mock survey completed by Week 2; all POCs drafted by Week 3; remediation underway by Week 4

- External: None

- Note: If accreditation survey is scheduled, verify exact date and count backward

## Month 11: Final Preparation & Staff Readiness

### Compliance Milestones

- ☐ Complete all remediation from mock survey findings

- ☐ Conduct second mini-mock focusing on top deficiency areas

- ☐ Ensure all staff can articulate their roles in key policies

- ☐ Verify all physical environment items (signage, fire equipment, emergency supplies)

- ☐ Confirm all documentation binders/systems are organized and accessible

- ☐ Prepare surveyor welcome packet

### Required Documentation

| Document | CMS Reference | Status | Due Date | Owner |
| --- | --- | --- | --- | --- |
| Remediation Completion Verification | All sections | ☐ Not Started | Month 11, Week 2 | Compliance Lead |
| Staff Competency Attestations | §416.46 | ☐ Not Started | Month 11, Week 2 | Clinical Lead |
| Surveyor Welcome Packet | N/A | ☐ Not Started | Month 11, Week 3 | Administrator |
| Document Index (master list of all policies) | N/A | ☐ Not Started | Month 11, Week 1 | Compliance Lead |
| Final Environment Walkthrough Report | §416.44 | ☐ Not Started | Month 11, Week 3 | Facilities |
| Emergency Contact List (updated) | §416.54 | ☐ Not Started | Month 11, Week 1 | Administrator |

### Submission Deadlines

- Internal: All remediation 100% complete by Week 2; facility tour-ready by Week 3

- External: Submit accreditation application (if initial survey) per accrediting body timeline

- AAAHC: Application typically required 90–120 days before desired survey date

## Month 12: Survey Readiness & Continuous Compliance

### Compliance Milestones

- ☐ Conduct final walkthrough — facility must be “survey-ready” every single day

- ☐ Verify all logs are current (temperature, sterilization, fire drills, equipment)

- ☐ Confirm QAPI data is current with at least 2 completed improvement projects

- ☐ Review all meeting minutes (Governing Body, QAPI, IC, Peer Review)

- ☐ Establish ongoing compliance calendar for next 12 months

### Required Documentation

| Document | CMS Reference | Status | Due Date | Owner |
| --- | --- | --- | --- | --- |
| Final Compliance Status Report | All sections | ☐ Not Started | Month 12, Week 1 | Compliance Lead |
| QAPI Annual Report | §416.43 | ☐ Not Started | Month 12, Week 2 | Quality Lead |
| Annual IC Risk Assessment (completed) | §416.51 | ☐ Not Started | Month 12, Week 1 | IC Officer |
| Governing Body Annual Review Minutes | §416.41 | ☐ Not Started | Month 12, Week 2 | Administrator |
| Year 2 Compliance Calendar (draft) | N/A | ☐ Not Started | Month 12, Week 4 | Compliance Lead |
| Accreditation Application (if applicable) | Per accreditor | ☐ Not Started | Per accreditor deadline | Administrator |

### Submission Deadlines

- Internal: All documentation finalized and indexed

- External: Accreditation survey may occur during this month or Month 1 of next cycle

- CMS: Medicare enrollment revalidation — verify revalidation due date on PECOS

## Recurring Monthly Requirements

The following items must be completed every month regardless of where you are in the 12-month cycle:

| Task | Frequency | CMS Reference | Owner |
| --- | --- | --- | --- |
| Governing Body meeting (or documented communication) | Monthly or per bylaws | §416.41 | Administrator |
| QAPI data collection and review | Monthly | §416.43 | Quality Lead |
| Infection surveillance tracking | Monthly | §416.51 | IC Officer |
| Medication storage temperature logs | Daily (reviewed monthly) | §416.48 | Clinical Lead |
| Equipment maintenance checks | Per manufacturer schedule | §416.44 | Facilities |
| Sterilization biological indicator testing | Per policy (weekly minimum) | §416.51 | IC Officer |
| Fire/safety rounds | Monthly | §416.44 | Safety Officer |
| Crash cart checks | Per policy (daily when OR active) | §416.44 | Clinical Lead |
| Controlled substance counts | Per policy (each shift minimum) | §416.48 | Clinical Lead |
| Staff competency observations | Ongoing | §416.46 | Clinical Director |

## Recurring Quarterly Requirements

| Task | Quarter | CMS Reference | Owner |
| --- | --- | --- | --- |
| Fire drill (documented) | Q1, Q2, Q3, Q4 | §416.44 | Safety Officer |
| QAPI committee meeting with minutes | Q1, Q2, Q3, Q4 | §416.43 | Quality Lead |
| Infection control committee review | Q1, Q2, Q3, Q4 | §416.51 | IC Officer |
| Policy review (rotating section each quarter) | Q1, Q2, Q3, Q4 | All | Compliance Lead |
| Emergency preparedness drill | Q1, Q2, Q3, Q4 | §416.54 | Administrator |
| Credentialing file spot-check (3 files minimum) | Q1, Q2, Q3, Q4 | §416.45 | Compliance Lead |
| Environment of care rounds | Q1, Q2, Q3, Q4 | §416.44 | Facilities |

## Recurring Annual Requirements

| Task | Deadline | CMS Reference | Owner |
| --- | --- | --- | --- |
| Infection Control Risk Assessment | Anniversary of last assessment | §416.51 | IC Officer |
| Emergency Preparedness Plan review and update | Annually | §416.54 | Administrator |
| QAPI Annual Effectiveness Review | End of compliance year | §416.43 | Quality Lead |
| Credentialing/re-privileging cycle | Per policy (typically every 2 years) | §416.45 | Medical Director |
| HIPAA risk assessment | Annually | HIPAA Security Rule | Privacy Officer |
| Policy manual comprehensive review | Annually | All | Compliance Lead |
| Life Safety Code inspection | Annually (or per AHJ) | §416.44 | Facilities |
| Fire alarm and suppression system inspection | Annually | NFPA | Facilities |
| Medical gas system certification | Annually | NFPA 99 | Facilities |
| Staff TB screening / health requirements | Annually (or per policy) | §416.51 / OSHA | IC Officer |
| Governing Body annual organizational review | Annually | §416.41 | Administrator |

## Key Contacts & Resources

| Resource | URL / Contact | Purpose |
| --- | --- | --- |
| CMS State Operations Manual, Appendix L | cms.gov — Search “Appendix L” | Official ASC survey guidance |
| AAAHC Standards | aaahc.org | Accreditation standards handbook |
| State Health Department | Varies by state | Licensure, reportable events |
| NPDB | npdb.hrsa.gov | Provider background checks |
| PECOS | pecos.cms.hhs.gov | Medicare enrollment management |
| OSHA | osha.gov | Workplace safety requirements |
| Fire Marshal (local) | Varies | Life Safety Code inspections |

## Document Version Control

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | Initial Release | ASC Compliance Team | Original 12-month roadmap |

This document is part of the ASC Compliance Manual — Tier 1: Essential Compliance Package ($97). For the complete system including staff training matrices, policy templates, and quarterly update frameworks, upgrade to Tier 2: Complete Certification System ($197).